## Read Me
Definitions - Different Sheets used in Business Process Review
Products | It demonstrates model bank products being covered in BPR sheet and update bank product list if required
Processes | All Model Bank / Local Processes relevant to bank business are mentioned and discussed with the bank
Scoping Gaps | This sheet contains Gaps, Back to core items – Customization that could be replaced by Temenos core features, Existing customizations that will be retrofitted to Temenos etc.
Follow Up Sheet | Items require follow up are recorded in this sheet for any action and decision to reflect in scoping gap sheet

## Sign Off
# | Name | Role | Company | Signature | Date

## Version History
S.No | Version No | Created by | Creation Date | Amendment Date | Amended By | Amendment Reason | Amendment Description
1
2
3
4
5
Note: If there are any amendments to be made in the BPR sheet then please change the version name to 1.1 and so on. Amendment details should be properly given. If possible should be highlighted with different color.

## Products
Process ID | PRODUCT | OVERVIEW | FEATURES | CURRENCY | INTEREST RATE | PA | Start Slippage | Duration Slippage | Process Discussion Status | Comments
| T-24 Transact IFRS 9 Module | IFRS9 Classification, Measurement & Impairment. | IFRS9 Classification, Measurement & Impairment. | N/A | N/A | N/A

## Processes
Process ID | Process Name | Level | Plan Start Date | Plan Finish Date | Duration (Hrs) | Actual Start Date | Actual Finish Date | Start Slippage | Duration Slippage | Process Discussion Status | Comments
Classification of Financial Instruments
| Amortised Cost - (AMC) | As per MB
| Fair Value through Other Comprehensive Income - (FVTOCI) | As per MB
| Fair Value through Profit & Loss - (FVTPL) | As per MB
| Fair Value for Contigent (Asset / Off-Balance Sheet) | As per MB
Impairment Processing
| Stage 1: Initial Recognition | GAP Identified | [8 empty] | Development Required as per policy document of the DFI
| Stage 2: Significant Increase in Credit Risk | GAP Identified | [8 empty] | Development Required as per policy document of the DFI
| Stage 3: Credit Impaired | GAP Identified | [8 empty] | Development Required as per policy document of the DFI
Parameter Setup & Configuration
| ST.REGULATORY.PARAMETER | As per MB | [8 empty] | Defines the current and previous rule book of the regulation.
| IAS.CLASSIFICATION | As per MB | [8 empty] | Defines the business models of IFRS reporting classification.
| IFRS.PARAMETER | As per MB | [8 empty] | Defines the effective date of applicability of IFRS 9 accounting entries. This Parameter is defined at Branch Level.
| IFRS.ACCT.METHODS | As per MB | [8 empty] | Defines the rules / activities / accounting methods or events on the Business Models.
| IFRS.POSTING.DETAILS | As per MB | [8 empty] | Defines the rules for accounting i.e. Categories on the accounting methods.
| IFRS.EVENT.TYPE | As per MB | [8 empty] | Records description of various events that may occur during the life of a contract. Like Disbursal, Repayment, Rollover, Charges, Rate Change, Maturity Date Change, Schedule Change, etc.
| IFRS.SUB.TYPE | As per MB | [8 empty] | System links the IFRS.ACCT.METHODS to IFRS.POSTING.DETAILS.
| IFRS.ACCRUAL.PARAM | As per MB | [8 empty] | Defines the frequency for generating IFRS related accounting entries. This Parameter is defined Branch wise.
| PV.LOAN.CLASSIFICATION & PV.MANAGEMENT | GAP Identified | [8 empty] | Development Required in PV.Management as per policy document of the DFI
| PV.ASSET.DETAIL & PV.CUSTOMER.DETAIL & PV.PROFILE | GAP Identified | [8 empty] | Development Required in PV Asset Detail and PV Customer Detail as per policy document of the DFI
Enquiries
| Classified by Business Model (AMC, FVTOCI & FVTPL) | As per MB
| Classified by Stage | As per MB
| Classified by Product | As per MB
| Classified by Application | As per MB

## Product Config (hidden)
[5 empty] | Mandatory Information |  |  |  | Note: Customer & Accounting Property are Always Mandatory
Mandatory for Product Configuration
[60 empty] | Mandatory only in case of charges present in the product | [21 empty] | If Applicable
PRODUCT STRUCTURE |  |  | ACCOUNT | [6 empty] | OFFICERS |  |  |  | LIMIT |  |  |  |  | PROFIT | [9 empty] | TERM.AMOUNT | [5 empty] | PAYMENT RULES / PAYOUT RULES | [6 empty] | PAYMENT SCHEDULE | [5 empty] | CLOSURE | [5 empty] | ELIGIBILITY | [5 empty] | CHARGE | [10 empty] | ACTIVITY MAPPING |  | SETTLEMENT | [6 empty] | ACTIVITY.RESTRICTION |  | ROLL OVER
Product Group | Product Level | Currency | Category | Account Title | Base Date Type | Date Convention | Inactive Months | Arr Link | Input Type | Primary Officer | Other Officer - Role | Arr Link | Input Type | Default Limit Reference | Single Limit Y/N | Allow Netting | Arr Link | Input Type | Day Basis | Interest Calculated on | Fixed Rate | Variable Rate | Compounding | Calculation Source | Accrual Rule | PL Category | Arr Link | Input Type | Cancel Period | Cooling Period | Term | Amount | Arr Link | Input Type | Transaction activity | Application Type | Application Order | Sequence | Remainder activity | Arr Link | Input Type | Repayment Type | Repayment Method | Repayment Frequency | Arr Link | Input Type | Combine Bills | Closure Type | Closure Period | Closure Method | Posting Restriction | Arr Link | Input Type | Eligibility Rules | On online validation failure Produce Error / Override | On Review Failure Ignore / Change Product | Perform Review on Customer Static Changes | Perform Periodic Review / Frequency | If not Eligible change to this product | Charge Name | Description | Charge Type | Charge calculated on (if variable) | Fee range for variable | Schedule (Frequency) | Calculatoin Source | Activity Based | PL category | Arr Link | Input Type | Transaction | Activity | Account Debit / Payin Rule | Payment Type | Payin Definition | RC Type | Payout Property | Arr Link | Input Type | Periodic Attribute | Activity | Change Activity | Change Date Type | Change Period
[65 empty] | Online + schedule + amortise |  | Event base | Accounting

## Overdue Condition (hidden)
Overdue Condition
Bill Type | Status | Aging Type | Aging Number | Notice Days | Frequency | Age All | Susp | Status Movement | Move Balance | Effective | Agreement Status
INSTALLMENT | Pre - Grace | Days / Bills | 1 |  |  | YES/NO | YES | YES/NO | YES/NO | Due / Status
Grace
Delinquent
NAB

## RC Sheet (hidden)
RC Condition | [6 empty] | RC Priority |  |  |  | RC Product Priority |  | RC Contract Priority
Description | Retry Freq | Retry Attempts | Retry Period | Retry Option | Txn Type | Date Convention | Def Prev Settle | Prev Settle | System ID (OR) AA Product Group |  | AA Product | Aa Contract Party | Due Type | Due Rule
Business day Frequency | Daily, Weekly, Monthly etc. | No Of Days | End of this Month | Partial, None | FT.TXN.TYPE.CONDITION | FWD / BWD | YES/NO | YES/NO | AA | HOME.EQUITY | Personal Loan | AA | combined by | Date
|  |  | End of next mont etc. | End.partial | Transaction Type | [7 empty] | Sort By Date | OLDEST /NEWEST
[13 empty] | Sort By Amount | LARGEST / SMALLEST

## Scoping Gaps
WS Ref | Description | Remarks for Understanding Purpose | Remarks | Process Reference # | Gap Number | Process Name | Contact person | Raised by (Department) | MoSCoW Classification | Gap Category | Internal Gap Type | Bank Gap Type | Requirement Type | Gap Effort | Gap Status | Actions/ Comments | Functional / high Level Solution | Workshop Date | Man Days (Estimate) | Impact (Cost) | Impact (Time) | Man Days (New Estimate) | Dropped In | Dropped Date
[6 empty] | IAS.CLASSIFICATION | [5 empty] | Configuration
A
1
2
3
4
B
1
2
3

## Followup Sheet
S. No. | Date Raised | Gap Reference | Process Reference | Task Description | Priority | Status | Responsibility | Person To be Contacted | Category | Expected End Date | Last Modified Date | Next Followup Date | Actual End Date | Action / Comments | Aging | TAT

## Drop Down Fields (hidden)
MoSCoW | Scoping Gaps | Scoping Gaps | Level
MUST Have | Build IP | Not Defined Yet | As per MB
SHOULD Have | Delivered | Regulatory | GAP Identified
COULD Have | Other Country Requirement | Bank Requirement | As per CBO
WON'T Have | Moved to Other Stream | Sharia Compliant
To be Discussed
Effort |  |  | New Gaps
Low | Gap Status |  | Duplicate
Medium | Open |  | New Requirement
High | Dropped |  | Moved to Future Release
| Agreed |  | Details Required
Type | Workaround |  | Dropped
Retrofitted/Taken over as such into R19 |  | Gap Priority | Moved to Other Stream
Configuration | Process Status | High | To be Discussed
Parameterisation | Not Started | Medium | Features List Requirement
Customization | In Progress | Low | BSD Required
| Completed |  | BSD Delivered
| Deferred | FSD Status | Change Request
Category (Follow Up) |  | FSD Under Development | Item Status
Deliverables | Follow Up Status | FSD Review 1 | Critical
Tech Decision | Open | FSD Review 2 | Needs Attention
Business Decision | Closed | FSD Review 3 | On Track
Extra Discussion |  | Pending Sign-off
| BRD Status | Signed-off
Owner | BRD Under Development |  | Priority
Client | BRD Review | Workshop Attendance | Priority 1
NDC | Pending Sign-off | N/A | Priority 2
Temenos | Signed-off | Yes | Priority 3
| Dropped by Bank | No
Local Development | Requirement Type |  | RAG Status
Retrofitted/ Taken over as such into R19 | Existing - Manual |  | On Track
Discarded and Moved back to core | Existing - System |  | Needs Attention
Not Required anymore to be dropped | New Requirement |  | Critical

## Legend (hidden)
Description of Drop Down Fields - Scoping Gap Sheet
Description
| Gap Category | Not Defined Yet | Category is to be identified
|  | Regulatory | As per regulations
|  | Bank Requirement | Specific to bank internal process or User Wishlist
RFP Requirement
|  | Sharia | It is based on sharia compliant
| Gap Type | Retrofitted/Taken over as such into R19 | Existing development moved to new release
|  | Configuration | Can be addressed through enquiry, versions, composite screens etc
|  | Parameterisation | Can be done at TAABS Level, through any local template
|  | Customization | Development required
Back to Core
| Requirement Type | Existing - Manual | Currently being addressed as a manual process
|  | Existing - System | Currently it is available in bank existing system
|  | New Requirement | It is a new requirement , can be bank specific, regulatory, sharia etc.
| Gap Effort | Low | 1-3 Days
|  | Medium | 3-10 Days
|  | High | > 10 Days
| Gap Status | Open | Decision to be made
|  | Dropped | Functionality not required
|  | Agreed | Gap has been accepted
|  | Workaround | The Workaround or Standard Model Bank Process has been accepted by the users
Description of Drop Down Fields - Scoping Gap Sheet
| Priority | Low | Does not impact on sign off
|  | Medium | Important but can be addressed in BRD
|  | High | Must be addressed to close and sign off BPR sheet
| Status | Open | Item still under follow up, action to be taken
|  | Closed | Requirement provided, decision has been made
| Responsibility | Client | Client to Respond
|  | NDC | NDC to Respond
|  | Temenos | Other stakeholder to respond, Like Temenos, 3rd Party client etc
| Category | Deliverable
Technical Decision
Business Decision
Need Further discussion
| MoSCow | MUST Have
SHOULD Have
COULD Have
WON'T Have
Description of Drop Down Fields - Product Config Sheet
| Product Level | Parent
Child
| Arr Link | Tracking
Non Tracking
| Input Type | Negotiable
Non Negotiable
| Date Convention | forward
backward
calendar
forward same month
| Interest Day Basis | A1 360/360
A2 30/360
A3 30/360
A4 30/360
B 366/360
C 366/366
C2 366/366
D 360/366
E 366/365
E1 365/365
F 360/365
F1 360/365
F2 30/365
G 366/364
H 30/356
S SPECIAL
W 252/252
W1 21/252
| Closure Type | None
Balance
Maturity
| Payin Rule | Full
Partial
None
| Accrual Rule | Both
First
Insurance
Last
| Closure Method | None
Automatic
Manual
| Single Limit | Yes
No
| Base DateType | Agreement
Start
| charge type | Fixed
Variable