## Read Me
Definitions - Different Sheets used in Business Process Review
Products | It demonstrates model bank products being covered in BPR sheet and update bank product list if required
Processes | All Model Bank / Local Processes relevant to bank business are mentioned and discussed with the bank
Scoping Gaps | This sheet contains Gaps, Back to core items – Customization that could be replaced by R21 core features, Existing customizations that will be retrofitted to R21 etc.
Follow Up Sheet | Items require follow up are recorded in this sheet for any action and decision to reflect in scoping gap sheet

## Sign Off
# | Name | Role | Company | Signature | Date
1
2
3
4
5

## Version History
S.No | Version No | Created by | Creation Date | Amendment Date | Amended By | Amendment Reason | Amendment Description
1 | 1 | Muneeb Ahmed | 2024-08-11 | - | - | - | -
Note: If there are any amendments to be made in the BPR sheet then please change the version name to 1.1 and so on. Amendment details should be properly given. If possible should be highlighted with different color.

## Products (hidden)
Product ID | PRODUCT | OVERVIEW | FEATURES | CURRENCY | INTEREST RATE | PA | Start Slippage | Duration Slippage | Process Discussion Status | Comments

## Processes
Process ID | Process Name | Level | Plan Start Date | Plan Finish Date | Actual Start Date | Actual Finish Date | Start Slippage | Duration Slippage | Process Discussion Status | Comments
WS05-LI-BM | Limit
WS-LI-TA-01 | Setup Limit- Limit Reference | As per MB | 2024-08-08 | 2024-08-08 | 2024-08-08 | 2024-08-11 |  |  | Not Yet Started
WS-LI-TA-02 | Global Limit | As per MB | 2024-08-08 | 2024-08-08 | 2024-08-08 | 2024-08-11 |  |  | Not Yet Started
WS-LI-TA-03 | Limit Products Hierarchy | As per MB | 2024-08-08 | 2024-08-08 | 2024-08-08 | 2024-08-11 |  |  | Not Yet Started
WS-LI-TA-04 | Multi level Sub Products | As per MB | 2024-08-08 | 2024-08-08 | 2024-08-08 | 2024-08-11 |  |  | Not Yet Started
WS-LI-TA-05 | Revolving and Non revolving Limits | As per MB | 2024-08-08 | 2024-08-08 | 2024-08-08 | 2024-08-11 |  |  | Not Yet Started
| Limit Menu | [7 empty] | Not Yet Started
WS-LI-TA-06 | Create Secured Limit | As per MB | 2024-08-08 | 2024-08-08 | 2024-08-08 | 2024-08-11 |  |  | Not Yet Started
WS-LI-TA-07 | Create Unsecured Limit | As per MB | 2024-08-08 | 2024-08-08 | 2024-08-08 | 2024-08-11 |  |  | Not Yet Started
WS-LI-TA-08 | Maintain/Reverse Limit | As per MB | 2024-08-08 | 2024-08-08 | 2024-08-08 | 2024-08-11 |  |  | Not Yet Started
WS-LI-TA-09 | Change Customer Liability | As per MB | 2024-08-08 | 2024-08-08 | 2024-08-08 | 2024-08-11 |  |  | Not Yet Started
WS-LI-TA- | Sub Allocate Limit | As per MB | 2024-08-08 | 2024-08-08 | 2024-08-08 | 2024-08-11 |  |  | Not Yet Started
WS-LI-TA-11 | Authorise/Delete/Reject Limit | As per MB | 2024-08-08 | 2024-08-08 | 2024-08-08 | 2024-08-11 |  |  | Not Yet Started
WS-LI-TA-12 | Authorise/Delete Limit Sub Allocation | As per MB | 2024-08-08 | 2024-08-08 | 2024-08-08 | 2024-08-11 |  |  | Not Yet Started
WS-LI-TA-13 | Other | As per MB | 2024-08-08 | 2024-08-08 | 2024-08-08 | 2024-08-11

## Scoping Gaps
Business Process Review Sheet - Limit Management
WS Ref | Description | Process Reference # | Gap Number | Entity | Process Name | Raised by (Department) | MoSCoW Classification | Gap Category | Gap Type | Requirement Type | Gap Effort | Gap Status | Actions/ Comments | Functional / high Level Solution | Workshop Date | Man Days (Estimate) | Impact (Cost) | Impact (Time) | Man Days (New Estimate) | Dropped In | Dropped Date | NDC Comments
WS-LI-TA | All limit reference will be set to non-revolving. Bank currently have four (4) products. | WS-LI-TA-01 | WS-LI-TA-01 | TA | Setup Limit- Limit Reference | Bank | should Have | Bank Requirement | Configuration | New Requirement | Medium | Open |  |  | 2024-08-08
WS-LI-TA | For Limit product fixed will be set as default | WS-LI-TA-01 | WS-LI-TA-02 | TA | Global Limit | Bank | should Have | Bank Requirement | Configuration | New Requirement | Medium | Open |  |  | 2024-08-08
WS-LI-TA | Separate Category code for each bank's product. | WS-LI-TA-01 | WS-LI-TA-03 | TA | Limit Products Hierarchy | Bank | should Have | Bank Requirement | Configuration | New Requirement | Medium | Open |  |  | 2024-08-08
WS-LI-TA | There is no group loan in the bank currently | WS-LI-TA-13 | WS-LI-TA-04 | TA | Multi level Sub Products | Bank | should Have | Bank Requirement | Configuration | New Requirement | Medium | Open |  |  | 2024-08-08

## Followup Sheet
S. No. | Date Raised | Gap Reference | Process Reference | Task Description | Priority | Status | Responsibility | Person To be Contacted | Category | Expected End Date | Last Modified Date | Next Followup Date | Actual End Date | Action / Comments | Aging | TAT
1

## Limit Product and Structure
Note: Limit Reference ID may change in the final version.
Limit Reference will be set up on txn.ref.
| Limit Level | Limit Products | Limit Product Description
Limit Reference | PARENT | 1400 | TA Personal Finance
| CHILD | 1410 | TA Personal Finance
Limit Reference | PARENT | 1500 | TA Ijarah Financing
| CHILD | 1510 | TA Ijarah Financing
Limit Reference | PARENT | 1600 | TA Home Finance
| CHILD | 1610 | TA Home Finance
Limit Reference | PARENT | 1700 | TA Murahbah Finance
| CHILD | 1710 | TA Murahbah Finance

## Legend (hidden)
Description of Drop Down Fields - Scoping Gap Sheet
Description
| Gap Category | Not Defined Yet | Category is to be identified
|  | Regulatory | As per regulations
|  | Bank Requirement | Specific to bank internal process or User Wishlist
|  | Sharia | It is based on sharia compliant
| Gap Type | Configuration | Can be addressed through enquiry, versions, composite screens etc
|  | Parameterisation | Can be addressed through enquiry, versions, composite screens etc
|  | Customization | Development required
| Requirement Type | Existing - Manual | Currently being addressed as a manual process
|  | Existing - System | Currently it is available in bank existing system
|  | New Requirement | It is a new requirement , can be bank specific, regulatory, sharia etc.
| Gap Effort | Low | 1-3 Days
|  | Medium | 3-10 Days
|  | High | > 10 Days
| Gap Status | Open | Decision to be made
|  | Dropped | Functionality not required
|  | Agreed | Gap has been accepted
|  | Workaround | The Workaround or Standard Model Bank Process has been accepted by the users
Description of Drop Down Fields - Scoping Gap Sheet
| Priority | Low | Does not impact on sign off
|  | Medium | Important but can be addressed in BRD
|  | High | Must be addressed to close and sign off BPR sheet
| Status | Open | Item still under follow up, action to be taken
|  | Closed | Requirement provided, decision has been made
| Responsibility | Client | Client to Respond
|  | NDC | NDC to Respond
|  | Anabatic | Other stakeholder to respond, Like Temenos, 3rd Party client etc
Temenos
| Category | Deliverable
Technical Decision
Business Decision
Need Further discussion
| Process Discussion | Not Yet Started
Completed
Deferred
In Progress
| Level | As per MB
Gap Identified
| ENTITY | PK-ISLAMIC
PK-CONVENTIONAL
UAE
PK-ALL
ALL